## Planning
Task | Days since start | Days till completion | Start date | End date | Description | Who? | Assignment
1 | 0 | 1 | 2020-04-03 | 2020-04-04 | Database setup (MongoDB) | Thomas | 1
2 | 0 | 7 | 2020-04-03 | 2020-04-10 | Semi-supervised painting detection (ONLY script) | Gillis, Jochen, Andreas | 1
3 | 0 | 7 | 2020-04-03 | 2020-04-10 | Calibration matrix setup | Pieter-Jan | 2
4 | 7 | 1 | 2020-04-10 | 2020-04-11 | Integration script-database | Thomas | 1
5 | 8 | 2 | 2020-04-11 | 2020-04-13 | Research: data structure (e.g. what to save?) | Gillis, Jochen | 1
6 | 10 | 7 | 2020-04-13 | 2020-04-20 | Unsupervised painting detection | Thomas, Gillis, Jochen, Andreas | 2
7 | 17 | 2 | 2020-04-20 | 2020-04-22 | Calculate accuracy measures (FP, FN, …) |  | 2
8 | 17 | 3 | 2020-04-20 | 2020-04-23 | Determine a sharpness metric: delete unusable frames | Pieter-Jan | 2
9 | 17 | 2 | 2020-04-20 | 2020-04-22 | Predict room with test images |  | 2
10 | 17 | 2 | 2020-04-20 | 2020-04-22 | Research: how many fps do we need to process? |  | 2
11 | 20 | 2 | 2020-04-23 | 2020-04-25 | Predict room with videos |  | 2
12 | 22 | 2 | 2020-04-25 | 2020-04-27 | Determine keypoints in images (and save to db) |  | 3
13 | 22 | 2 | 2020-04-25 | 2020-04-27 | Determine feature vectors in images (and save to db) |  | 3
14 | 24 | 1 | 2020-04-27 | 2020-04-28 | Comparison: images assignment 1 with itself |  | 3
15 | 24 | 1 | 2020-04-27 | 2020-04-28 | Comparison: images assignment 2 with images assignment 1 |  | 3
16 | 25 | 3 | 2020-04-28 | 2020-05-01 | Localization of user in test pictures |  | 4
17 | 25 | 3 | 2020-04-28 | 2020-05-01 | Localization of user in videos ignoring current room |  | 4
18 | 28 | 3 | 2020-05-01 | 2020-05-04 | Localization of user in videos according to current room |  | 4
19 | 31 | 4 | 2020-05-04 | 2020-05-08 | Indicate location probabilties on fancy image |  | 5
20 | 35 | 2 | 2020-05-08 | 2020-05-10 | Prepare demo |  | 5
Formulas:
End date = [Start date]+[Days till completion]
Start date = [Start date, row above]
Start date = [End date, row above]